## Summary
Summary
Everything below calculates from the Risk Register tab. Only the two yellow cells are meant to be edited.
Rating bands
High if score is at least | 15 | Score is Likelihood x Impact, so the maximum is 25. 15 or more means likely and serious.
Medium if score is at least | 8 | Anything below the Medium line is rated Low.
Where the register stands
Risks listed | 20 | All risks in the register.
High risks | 4 | Score at or above the High line.
Medium risks | 14
Low risks | 2
High risks still open | 4 | High risks not yet Mitigated or Accepted. Aim for zero before go-live.
Risks without an owner | 20 | Every risk needs a named owner.
Average score | 11.15 | Falls as risks are re-scored after mitigation.
Highest score | 16
Sources behind the acceptance criteria
Google Search Central, Site moves with URL changes: developers.google.com/search/docs/crawling-indexing/site-move-with-url-changes
Google Search Central, Redirects and Google Search: developers.google.com/search/docs/crawling-indexing/301-redirects
Google Search Central, Managing crawling of faceted navigation URLs: developers.google.com/search/docs/crawling-indexing/crawling-managing-faceted-navigation
Adobe Commerce, Category URL rewrites: experienceleague.adobe.com/en/docs/commerce-admin/marketing/seo/url-rewrites/url-rewrite-category
Starting likelihood and impact scores are Ingold's working estimates, not measured data. Re-score them for your store.

## Risk Register
SEO migration risk register: Magento category pages
Built for relaunches, replatforms and large catalogue restructures. Starting scores are typical for a mid-sized Magento store, so re-score each risk for yours.
How to use it: edit only the yellow cells with blue text (Likelihood, Impact, Owner, Status, Notes). Score, Rating and the Summary tab recalculate. Rating bands are set on the Summary tab.
ID | Area | Risk | How it shows up after launch | Likelihood (1-5) | Impact (1-5) | Score | Rating | Pre-launch check | Acceptance criterion | Owner | Status | Notes
R01 | Redirects | Top category URLs missing from the map | A Tier 1 category isn't mapped, so its old URL returns a 404 or drops onto the home page and the ranking goes with it. | 3 | 5 | 15 | High | Compare the Tier 1 list with the map. Crawl every old URL on staging and record the status code. | Every Tier 1 URL is mapped. None returns a 404 unless the revenue owner has signed it off. |  | Open
R02 | Redirects | Redirect points at the wrong or a weaker page | The destination loads fine but answers a different search, or is a thin page. Impressions for the old query fall and stay down. | 3 | 4 | 12 | Medium | Read each Tier 1 and Tier 2 destination next to the old page. Check that the intent matches. | Each mapped pair is reviewed by a person and approved. The reason is recorded in the map. |  | Open
R03 | Redirects | Redirect chains and loops from legacy rewrites | Rewrites left by earlier migrations stack up. Googlebot follows a long chain slowly, and some URLs loop or fail. | 4 | 3 | 12 | Medium | Export the url_rewrite table and flatten it. Crawl the old URL list and count hops. | One hop for every Tier 1 URL. No URL anywhere needs more than three hops. |  | Open
R04 | Redirects | Temporary 302 used where a 301 was meant | Search engines treat the old URL as still live, so the new one is slow to replace it in results. | 2 | 4 | 8 | Medium | Check the redirect type for every map row in the crawl output. | All permanent moves return 301 (or 308). Any 302 has a written reason. |  | Open
R05 | Redirects | Retired categories redirected to the home page | Many unrelated URLs land on one page. Little of their value carries over and users bounce. | 3 | 3 | 9 | Medium | Filter the map for destinations equal to the home page. | No retired URL goes to the home page by default. Each has a close equivalent, a 404 or a 410. |  | Open
R06 | Redirects | Redirects removed too early | Old URLs with links or bookmarks stop resolving a few months after launch. | 2 | 4 | 8 | Medium | Put a removal rule in the hosting runbook. Record the redirect review date. | Redirects stay live for at least 12 months. Longer where old URLs still earn links. |  | Open
R07 | Redirects | Backlinked category URLs not protected | Pages with strong referring domains change address without a precise redirect, and the link value is wasted. | 3 | 4 | 12 | Medium | Join backlink data to the map by URL. Sort by referring domains. | Every URL with meaningful backlinks has a one-to-one redirect or keeps its address. |  | Open
R08 | Page signals | Canonical tag points to the old URL, staging or a variant | New pages show as alternates of other URLs in Search Console and don't take over the ranking. | 3 | 5 | 15 | High | Crawl staging and extract the canonical for every mapped URL. Compare it with the page's own address. | Each Tier 1 and Tier 2 page carries a self-referencing canonical to the live domain. |  | Open
R09 | Page signals | Noindex or robots rule carried over from staging | Whole sections vanish from the index within days of launch. | 3 | 5 | 15 | High | Check robots.txt, meta robots and response headers on the production build before go-live. | No Tier 1 to Tier 3 page carries noindex. robots.txt allows the live category paths. |  | Open
R10 | Page signals | Title, H1 and intro copy lost on the new category template | The redirect works, but the page no longer says what the old one said, so rankings slip. | 4 | 4 | 16 | High | Compare the old and new title, H1 and intro text for every Tier 1 page. | Tier 1 pages keep their title, H1 and intro copy, or have a deliberate improvement signed off. |  | Open
R11 | Page signals | Internal links still point at old URLs | Menus, footers and body copy send every click through a redirect and weaken the signal to the new address. | 4 | 3 | 12 | Medium | Crawl staging for links to any URL on the old-URL list. | Menus, footer, breadcrumbs and body links use new addresses. Redirects are only a safety net. |  | Open
R12 | Structure | New navigation drops mid-level categories | Pages that were two clicks from the home page are now four, and lose internal link weight. | 3 | 4 | 12 | Medium | Compare click depth for Tier 1 and Tier 2 pages before and after on staging. | Tier 1 pages are no deeper in the new structure than in the old one. |  | Open
R13 | Structure | Merged categories lose long-tail rankings | Two categories that ranked for different searches are folded into one page that matches neither as well. | 3 | 4 | 12 | Medium | List the queries each old category ranks for. Check the merged page's copy covers them. | Each merge is approved with its target queries listed and covered on the new page. |  | Open
R14 | Faceted navigation | Filter URLs become crawlable and duplicate | The index fills with near-duplicate filter pages and crawl budget goes on them, not on the pages that earn money. | 3 | 4 | 12 | Medium | Count parameter URLs reachable from a crawl of staging. Review the robots.txt rules for filters. | A written rule says which filter URLs may be crawled and indexed. It is tested on staging. |  | Open
R15 | Faceted navigation | Filter pages with search demand blocked or redirected without parameters | A filter that ranked and sold (teak, say) is blocked, or its parameter is dropped in the redirect, so the ranking is lost. | 3 | 3 | 9 | Medium | Pull filter queries from Search Console. Check each old filter URL against its destination. | Each filter page with real demand has a landing page or a rule of its own, and the old URL reaches it. |  | Open
R16 | Faceted navigation | Paginated pages canonicalised to page one | Products listed only on deeper pages lose their route to being found. | 2 | 3 | 6 | Low | Check the canonical on pages two and three of a large category on staging. | Paginated pages follow the canonical rule agreed in the migration plan. |  | Open
R17 | Measurement | Analytics or Search Console set-up broken | Traffic looks lost because tracking stopped, or a real loss goes unseen. | 3 | 4 | 12 | Medium | Test tracking on staging. Verify the new property and sitemap in Search Console. | Revenue and landing page data are flowing on day one. Search Console is verified. |  | Open
R18 | Measurement | No baseline for rankings and organic revenue | After launch nobody can say whether a dip is normal or damage. | 4 | 3 | 12 | Medium | Export 12 months of landing page revenue and a fixed set of ranking terms for Tier 1 pages before launch. | A dated baseline file exists and is stored with the migration map. |  | Open
R19 | Measurement | Old sitemap submitted or new sitemap missing | Google is slow to find the new URLs. | 2 | 3 | 6 | Low | Check the new XML sitemap lists only live, canonical, indexable URLs. | The new sitemap is submitted on launch day and contains no redirected URLs. |  | Open
R20 | Platform | Server can't cope with the post-move crawl | Googlebot crawls heavily after a move. Slow responses or 5xx errors slow indexing. | 2 | 4 | 8 | Medium | Load-test category pages. Agree a monitoring window for the first two weeks. | Category pages respond normally under crawl load. 5xx errors are alerted on. |  | Open

## URL Mapping
Category URL migration map (template)
The rows below are ILLUSTRATIVE examples for a fictional garden furniture retailer. Replace them with your own URLs and figures.
Edit the yellow cells. 'Ready?' says Ready when the old URL takes one hop, the destination returns 200 and the new page has a self-referencing canonical. Add rows by copying the last row down.
Old URL | Tier (1-3) | Organic revenue, 12 months | Organic sessions, 12 months | Referring domains | Conversions, 12 months | New URL | Handling | Redirect hops (tested) | Destination status code | Self-referencing canonical? (Yes/No) | Ready? | Notes
/garden/furniture/dining-sets.html | 1 | 182400 | 41200 | 38 | 1020 | /garden-furniture/dining-sets/ | Exact match, 301 | 1 | 200 | Yes | Ready | Title, H1 and intro copy carried across.
/garden/furniture/rattan-sets.html | 1 | 121900 | 29800 | 52 | 690 | /garden-furniture/rattan-sets/ | Exact match, 301 | 1 | 200 | Yes | Ready | Strong backlinks. Direct single hop.
/garden/furniture/bistro-sets.html | 2 | 19800 | 7300 | 5 | 120 | /garden-furniture/small-space-sets/ | Merged, 301 | 1 | 200 | Yes | Ready | Merged with balcony sets. New copy covers both searches.
/garden/furniture/balcony-sets.html | 2 | 13800 | 4800 | 4 | 90 | /garden-furniture/small-space-sets/ | Merged, 301 | 2 | 200 | Yes | Check | Chain via an old rewrite. Flatten to one hop before launch.
/garden/lighting.html | 2 | 41300 | 15600 | 17 | 280 | /outdoor-lighting/ | Renamed, 301 | 1 | 200 | Yes | Ready | Same category under a better URL key. Update internal links.
/summer-sale-2023.html | 3 | 2100 | 900 | 14 | 15 | /sale/ | Parent fallback, 301 | 1 | 200 | Yes | Ready | No equivalent page. Kept for the 14 referring domains.
/garden/furniture.html?material=teak | 2 | 27500 | 9800 | 6 | 180 | /garden-furniture/teak/ | Filter promoted to landing page | 1 | 200 | Yes | Ready | Needs a server-level rule. A category rewrite drops the parameter.
/garden/furniture.html?price=100-200 | 3 | 300 | 120 | 0 | 2 | /garden-furniture/ | Retired filter, 301 to parent | 1 | 200 | Yes | Ready | No search demand. Blocked from crawling on the new build.